## Project Profile
Query Tracking Sheet Template
PVV/ETR01/TMP
Project Code | Team 4
Project Name | University Admission System
Prepared/Modified by | Role | Date of Preparation
Team 4 |  | 2017-11-06
Reviewed by | Role | Date of Review
Ashwini Shinde | Software Engineer | 2017-11-07
Approved by | Role | Date of Approval
N. Kathiresen | Mentor | 2017-11-07
Circulation List | ashu.a.gupta@capgemini.com ashwini.e.shinde@capgemini.com sharvari.more@capgemini.com srishty.saxena@capgemini.com podishetti.krishna@capgemini.com vipul.samala@capgemini.com zarana.matani@capgemini.com | Version Number of the template: 1.0
Version Number | 1

## Query Sheet
PROJECT GROUP 3:Survey Management System | GROUP 4 | UNIVERSITY ADMISSION SYSTEM
Query Tracking Sheet
Sr.No | Type | Module | Query Text | Reply Text | Raised By (Name) | Open (Date) | Reply By (Name) | Closed (Date) | Phase Raised In | Phase Closed in | CR (Y/N) | Status | Query TAT (Turn Around Time) in days
1 |  | Admin & MAC | Can the admin and mac change their user Id and password after successful login? | No. | Vipul Samala(135667) | 2017-10-04 | N. Kathiresan | 2017-10-23 | Requirement Analysis | Requirement Analysis | N | Closed | 2
2 |  | Applicant | Can we add an additional table called 'Universities' in the data base, which contains the details of the universities to be applied, so that we can use it to retrieve the required data? | Yes. | Ashwini Shinde(135695) | 2017-10-04 | N. Kathiresan | 2017-10-23 | Requirement Analysis | Requirement Analysis | N | Closed | 2
3 |  | Applicant | Does the applicant have right to select the interview date? | No. | Redin Krishna(135679) | 2017-10-04 | N. Kathiresan | 2017-10-26 | Requirement Analysis | Requirement Analysis | N | Closed | 2
4 |  | Applicant | Can the applicant Id be according to the course applied? | No, since it is auto generated. | Zarana Matani(135669) | 2017-10-04 | N. Kathiresan | 2017-10-26 | Requirement Analysis | Requirement Analysis | N | Closed | 2
5 |  | MAC | Should MAC notify the applicant his/her status of selection process through SMS? | No, since the applicant is given an option to check his/her status. | Ashu Gupta(135305) | 2017-10-04 | N. Kathiresan | 2017-10-26 | Requirement Analysis | Requirement Analysis | N | Closed | 2
6 |  | MAC | What should be the duration between applied date and interview date given by MAC? | It should be maximum of 10 days. | Srishty Saxena() | 2017-10-04 | N. Kathiresan | 2017-11-01 | Requirement Analysis | Requirement Analysis | N | Closed | 2
7 |  | Applicant | Does the applicant have any right to select the interview date? | No, It will be given by MAC. | Sharvari More(135430) | 2017-10-04 | N. Kathiresan | 2017-11-01 | Requirement Analysis | Requirement Analysis | N | Closed | 2
Note on B4: QC = Q by Client QP = Q by IGate
Note on L4: Has this query resulted in a CR (record shd be present in the CR tracking Sheet)
Note on M4: Open Active Closed On-hold
Note on N4: TAT is the difference in days between the time query is raised to the time query is closed. Average TAT can be included be in the weekly status report to the client